## Sheet1
Phase | Area | UAT ID | Scenario / Test Title | Preconditions | Test Steps | Expected Result | Role(s) | Evidence (Screenshots / Notes) | Status (Pass/Fail/Blocked)
Phase 7 - Chemicals & Permits | Chemicals - Register | P7-UAT-CHEM-01 | Create a new chemical in the register | Logged in as Org Admin. At least one site exists. | 1. Navigate to Chemicals > Register (/chemicals). 2. Click 'New Chemical'. 3. Fill in required fields: Name, CAS number, supplier, hazard classes, status. 4. Save the chemical. | New chemical appears in the register with correct details and status badge. | Admin | Screenshot of Chemical Register showing the new chemical row.
Phase 7 - Chemicals & Permits | Chemicals - Register | P7-UAT-CHEM-02 | Search and filter chemicals | At least 3 chemicals exist with different hazard classes and statuses. | 1. Navigate to Chemicals > Register. 2. Use search box to search by chemical name. 3. Apply filter by hazard class. 4. Apply filter by status (Active/Phase-out/Banned). | Search and filters correctly narrow the list; only matching chemicals are shown. | Admin / Manager | Before-and-after screenshots of the register with filters applied.
Phase 7 - Chemicals & Permits | Chemicals - Detail | P7-UAT-CHEM-03 | View chemical detail and GHS hazard icons | At least one chemical with multiple GHS hazard classes is created. | 1. From Chemical Register, click a chemical. 2. Open the Chemical Detail page. 3. Review the header, hazard icons, and meta data. | Chemical Detail displays correct name, CAS number, supplier, hazard icons for all assigned GHS classes, and status badge. | Admin / Manager / Worker (view) | Screenshot of Chemical Detail header showing hazard icons and metadata.
Phase 7 - Chemicals & Permits | Chemicals - SDS | P7-UAT-CHEM-04 | Upload and view SDS document for a chemical | Chemical exists. User has SDS file (PDF) stored locally. | 1. On Chemical Detail page, go to SDS / Documents section. 2. Click 'Upload SDS'. 3. Select SDS PDF and upload. 4. Save/update the record. 5. Click the SDS link to open/download the file. | SDS uploads successfully, appears in the list, and can be opened/downloaded without errors. | Admin / Manager | Screenshot showing SDS listed and, if possible, a view of the open document.
Phase 7 - Chemicals & Permits | Chemicals - SDS | P7-UAT-CHEM-05 | SDS expiry status and badge display | Chemical with SDS expiry date in the past and one with expiry in the future exist. | 1. Open Chemical Detail for a chemical with an expired SDS. 2. Observe SDS status badge. 3. Open another chemical with a valid SDS expiry date. 4. Compare badges. | Expired SDS shows an 'Expired' or warning badge; valid SDS shows 'In Date' or equivalent. Colours/icons clearly distinguish the states. | Admin / Manager | Screenshots of both chemicals: one with expired SDS, one with valid SDS.
Phase 7 - Chemicals & Permits | Chemicals - Locations | P7-UAT-CHEM-06 | Add storage locations for a chemical | At least one site exists; chemical exists. | 1. Open Chemical Detail page. 2. Navigate to Locations/Inventory section. 3. Add a new storage location, selecting site, location name, and typical/max quantity. 4. Save the location. 5. Add a second location at a different site or area. | Both locations appear in the list with correct site, location name, and quantity details. | Admin / Manager | Screenshot of Locations/Inventory section showing multiple entries.
Phase 7 - Chemicals & Permits | Chemicals - Locations | P7-UAT-CHEM-07 | Edit and remove a storage location | Chemical with at least one location entry exists. | 1. Open the chemical's Locations/Inventory list. 2. Edit an existing location (change quantity or name). 3. Save and verify the update. 4. Remove one location and confirm. | Edited location shows updated values. Removed location no longer appears. No errors shown. | Admin | Before-and-after screenshots of the location being edited and removed.
Phase 7 - Chemicals & Permits | Chemicals - Integration | P7-UAT-CHEM-08 | Link a chemical to an incident | An incident exists and at least one chemical exists. | 1. Open an Incident Detail page. 2. Use the 'Linked Chemicals' panel to add an existing chemical to this incident. 3. Save. 4. Open the Chemical Detail page. 5. Confirm the incident is listed in linked items. | Incident shows the chemical in its Linked Chemicals panel. Chemical Detail shows the incident under linked records. | Manager / Admin | Screenshots of Incident Detail and Chemical Detail showing the link.
Phase 7 - Chemicals & Permits | Chemicals - Integration | P7-UAT-CHEM-09 | Link a chemical to an inspection or action (if supported) | At least one inspection and one action exist; chemical exists. | 1. Open an Inspection or Action detail page (depending on Phase 7 design). 2. Use the linking UI to associate the chemical. 3. Save. 4. Check Chemical Detail to confirm links. | Chemical is correctly linked to the inspection/action and visible on both sides of the relationship. | Manager / Admin | Screenshot of linked chemical on the inspection/action + Chemical Detail.
Phase 7 - Chemicals & Permits | Permits - Types | P7-UAT-PERM-01 | Configure permit types | Logged in as Org Admin. | 1. Navigate to Admin > Permit Types (/admin/permit-types). 2. Create at least two permit types (e.g., Hot Work, Confined Space). 3. Define required fields/checklists as per UX. 4. Save changes. | New permit types appear in the list and are available when creating a permit. | Admin | Screenshot of Permit Types page showing configured types.
Phase 7 - Chemicals & Permits | Permits - Creation | P7-UAT-PERM-02 | Create a permit via the permit wizard | Permit types configured; at least one site exists. | 1. Navigate to Permits > New (/permits/new). 2. Go through the 3-step wizard: select type, fill mandatory fields, add controls/attachments. 3. Save the permit in 'Draft' or 'Submitted' state as per design. | Permit is created successfully, appears in the permit list with correct initial status and data. | Manager / Admin | Screenshot of the completed wizard and the permit row in the list.
Phase 7 - Chemicals & Permits | Permits - Lifecycle | P7-UAT-PERM-03 | Move a permit through full lifecycle | Permit exists in Draft or Submitted state. | 1. Open the Permit Detail page. 2. Transition status through the allowed path: Draft → Submitted → Approved → Active → Closed. 3. Attempt any disallowed transitions (e.g. Closed → Active) and observe behaviour. | Allowed transitions succeed and update state/history timeline. Disallowed transitions are blocked with a clear error or disabled UI. | Manager / Admin | Screenshot of State History timeline showing the full lifecycle.
Phase 7 - Chemicals & Permits | Permits - Controls | P7-UAT-PERM-04 | Complete and review permit control checklist | Permit exists in Active state with configured controls. | 1. Open the Permit Detail page. 2. Go to Controls/Checklist section. 3. Mark each required control as complete or set appropriate values. 4. Save. 5. Re-open the permit to verify saved checklist. | All control items save correctly and are displayed on subsequent views; no missing/incorrect values. | Manager / Admin | Screenshot of Control Checklist before and after completion.
Phase 7 - Chemicals & Permits | Permits - Countdown | P7-UAT-PERM-05 | Verify permit countdown/status indicators | Permit exists with a defined active period (start/end times). | 1. Open Permit Detail and Permit Board. 2. Observe countdown timers or due/expiry indicators for active permits. 3. Adjust system time or create permits with start/end around 'now' to see different states (e.g. upcoming, active, near expiry). | Countdown or time status indicators reflect correct time remaining or overdue state, both on the Permit Detail and Permit Board. | Manager / Admin | Screenshots of permits in different time states (upcoming, active, near expiry, expired/closed).
Phase 7 - Chemicals & Permits | Permits - Board | P7-UAT-PERM-06 | View and filter the Permit Board | Multiple permits exist across different sites, types, and statuses. | 1. Navigate to Permits > Board (/permits/board). 2. Verify that current/active permits are displayed. 3. Apply filters by site, permit type, and status. 4. Observe auto-refresh behaviour (if implemented). | Permit Board shows relevant permits; filters reduce the list correctly. Auto-refresh updates data without full page reload (if enabled). | Manager / Admin / Supervisor | Screenshots of Permit Board before and after filters, plus evidence of auto-refresh if possible (e.g., new permit appearing without refresh).
Phase 7 - Chemicals & Permits | Permits - List | P7-UAT-PERM-07 | Search and sort permits in the main list | Several permits exist with different IDs, types, statuses, and dates. | 1. Navigate to Permits > List (/permits). 2. Use search to find a permit by ID or title. 3. Sort by status, type, or date (depending on design). 4. Confirm order updates correctly. | Permit list search and sorting behave as expected, with correct rows and order. | Manager / Admin | Screenshots of the list before/after search and sort operations.
Phase 7 - Chemicals & Permits | Permits - Integration | P7-UAT-PERM-08 | Link a permit to an incident | At least one incident and one permit exist. | 1. Open an Incident Detail page. 2. Use the Linked Permits panel to add an existing permit. 3. Save. 4. Open the Permit Detail page. 5. Confirm the incident is listed as a linked entity. | Incident now shows the linked permit; Permit Detail lists the associated incident. Links navigate correctly between pages. | Manager / Admin | Screenshots of Incident Detail and Permit Detail with cross-links visible.
Phase 7 - Chemicals & Permits | Permits - Integration | P7-UAT-PERM-09 | Link permits to actions or inspections (if supported) | At least one permit, inspection, and action exist. | 1. Open an Action or Inspection detail page. 2. Link an existing permit using the provided UI. 3. Save. 4. Verify links on both the permit and the action/inspection side. | Permit is correctly linked and visible from both entities; clicking the link navigates to the related record. | Manager / Admin | Screenshot of linked permit on the action/inspection and on the Permit Detail page.
Phase 7 - Chemicals & Permits | Security & Multi-Tenancy | P7-UAT-SEC-01 | Verify chemicals are scoped per organisation | Two organisations exist with different sets of chemicals; test accounts for each org. | 1. Log in as an Admin of Org A and view Chemical Register. 2. Note visible chemicals. 3. Log in as an Admin of Org B. 4. Confirm chemicals from Org A do not appear and vice versa. | Chemical lists are strictly scoped by organisation; no cross-tenant visibility. | Admin (Org A & Org B) | Screenshots of Chemical Register for each org showing different data sets.
Phase 7 - Chemicals & Permits | Security & Multi-Tenancy | P7-UAT-SEC-02 | Verify permits are scoped per organisation | Two organisations exist with different sets of permits. | 1. Log in as an Admin of Org A and view Permits list and Permit Board. 2. Note visible permits. 3. Log in as an Admin of Org B. 4. Confirm permits from Org A do not appear and vice versa. | Permits are strictly scoped to the current organisation in all permit-related views. | Admin (Org A & Org B) | Screenshots of Permits pages for each org showing isolation.
Phase 7 - Chemicals & Permits | Security & Roles | P7-UAT-SEC-03 | Verify role-based access for chemical and permit admin functions | At least three test users: Admin, Manager, Worker. | 1. Log in as Admin and access all chemical and permit admin pages (e.g., Permit Types, Chemical Create/Edit). 2. Log in as Manager and attempt the same pages. 3. Log in as Worker and attempt to access those admin pages directly via URL. 4. Observe behaviour for each role. | Admin has full access; Manager has only the intended subset (e.g., may create permits but not configure permit types, depending on design); Worker is blocked from admin-only pages with clear messaging. | Admin / Manager / Worker | Screenshots of access allowed vs access denied for different roles.