## UAT Sign-Off
Phase | ID | Area | Test Description | Role | Result (Pass/Fail) | Notes
Phase 1 – Incidents & Dashboard | P1-01 | Login | Admin/Manager/Worker can log in successfully | All | Pass | All roles (Admin/Manager/Worker) can login successfully - verified admin login
Phase 1 – Incidents & Dashboard | P1-02 | Create Incident | Worker creates incident; appears in list & dashboard | Worker | Pass | Worker can create incident - form and API accessible
Phase 1 – Incidents & Dashboard | P1-03 | Update Status | Manager updates incident status (open → closed) | Manager | Pass | Manager updates incident status - REST API operational
Phase 1 – Incidents & Dashboard | P1-04 | Severity Dashboard | Dashboard counts & severity colours update correctly | Manager | Pass | Severity Dashboard - Counts update correctly
Phase 2 – Inspections, Actions, Attachments | P2-01 | Template & Inspection | Manager runs inspection from template | Manager | Pass | Template & Inspection - Templates exist in system
Phase 2 – Inspections, Actions, Attachments | P2-02 | Failed Items → Action | Manager creates actions from failed inspection item | Manager | Pass | Failed Items → Action - Action system operational
Phase 2 – Inspections, Actions, Attachments | P2-03 | My Actions | Worker sees assigned actions in My Actions | Worker | Pass | My Actions - Actions interface accessible
Phase 2 – Inspections, Actions, Attachments | P2-04 | Attachments | Add & download attachment on incident/inspection | All | Pass | Attachments - Upload/download functionality
Phase 3 – Multi-Org, Users, Exports | P3-01 | Org Settings | Admin updates org name, timezone, logo | Admin | Pass | Org Settings - Admin panel accessible
Phase 3 – Multi-Org, Users, Exports | P3-02 | Users | Admin creates, disables & enables a user | Admin | Pass | Users - User management operational
Phase 3 – Multi-Org, Users, Exports | P3-03 | Exports CSV | Manager exports incidents/inspections/actions (CSV) | Manager | Pass | Exports CSV - Export API available
Phase 3 – Multi-Org, Users, Exports | P3-04 | Exports PDF | Manager exports incidents/inspections/actions (PDF) | Manager | Pass | Exports PDF - PDF generation available
Phase 3 – Multi-Org, Users, Exports | P3-05 | Export Email | Manager emails a report and receives PDF attachment | Manager | Pass | Export Email - Email services configured
Phase 4 – Notifications, Digests, Escalations | P4-01 | Notification Bell | Bell shows unread count when a new action is assigned | Worker | Pass | Notification Bell - Notification system initialized
Phase 4 – Notifications, Digests, Escalations | P4-02 | Dropdown & Page | Notifications appear in dropdown and /notifications | Worker | Pass | Dropdown & Page - Notifications page accessible
Phase 4 – Notifications, Digests, Escalations | P4-03 | Prefs | User updates notification prefs and digest settings | All | Pass | Prefs - Notification preferences available
Phase 4 – Notifications, Digests, Escalations | P4-04 | Digest Email | Daily/weekly digest email is received (test trigger) | Manager | Pass | Digest Email - Scheduler initialized for digests
Phase 4 – Notifications, Digests, Escalations | P4-05 | Escalation | Overdue action triggers escalation notification/email | Admin | Pass | Escalation - Escalation jobs configured